## MasterSheet
Client Name | [9 empty] | Story Task | Complexity
Project Name |  |  | Execution lead | [6 empty] | Coding - New Feature | Low
Project Description |  |  | GenAi Champion | [6 empty] | Coding Enhancement | Medium
[10 empty] | Bug fixing | High
[10 empty] | Code Review | Very High
UT Scripts
Unique Id (it is not Jira-ID)/ Feature ID | Reference JIRA Id | Unique Story Description | Complexity | Efficiency Assumption |  |  | Prompt Mapping | Sprint | Type | DB Scripts Generation
|  |  |  | Min % | High % | Average % |  | DC4.1 | Functionality | Code Documentation
XLPT_0001 |  | Write New UI funcationality | Medium | 40% | 80% | 60% | No prompt templates available. But we have reusable code | DC4.2 | Tool limitation | DevOps Script -New
XLPT_0002 |  | Unit Testing | Medium | 45% | 80% | 62.5% | No prompt templates available. But we have reusable code | DC4.3 | Non-Development | DevOps Script -Enhancement
XLPT_0003 |  | API - create new / update existing | Medium | 50% | 80% | 65% | No prompt templates available. But we have reusable code | DC5.1 | Manual Testing | Test Cases Generation
XLPT_0004 |  | Decoder | High | 55% | 70% | 62.5% | No prompt templates available. But we have reusable code | DC5.2 |  | Test Scripts - New
XLPT_0005 |  | Regression Cypress | Medium | 50% | 80% | 65% | No prompt templates available. But we have reusable code | DC5.3 |  | Test Scripts - Enhancement
XLPT_0006 |  | MEMSQL ,DB | High | 60% | 80% | 70% | No prompt templates available. But we have reusable code |  |  | Test Scripts - Fix
XLPT_0007 |  | Java ,MicroServices | Medium | 70% | 90% | 80% | No prompt templates available. But we have reusable code |  |  | Test Script Review
XLPT_0008 |  | Analysis, Documentation and R&D | Medium | 80% | 100% | 90% | No prompt templates available. But we have reusable code |  |  | Code Analysis
XLPT_0009 |  | Devops | Medium | [6 empty] | Deployment
User Story Creation
Epic Creation
Acceptance TC
Design Documentation
RCA Documentation
Design Documentation
Design Review
ER Diagram
Project Mgmt - Planning
Project Mgmt - Estimation
Project Mgmt - Status Reporting
Project Mgmt - Documentation
Other

## Estimationplan
|  |  | Sprint | Total Original Estimate |  | Avg Projected Efficiency % | Total Projected Estimate | Total Effort Saved | LOE data
|  |  | DC5.1 | 1090 |  | 0.71111 | 120.034 | 814.966
|  |  | All | 1880 |  | 0.71111 | 120.034 | 814.966
Sprint | Jira id | Description | Matching unique ID | Total Estimate | Gen AI NA | Projected Efficiency % | Projected Estimate | Project Effort saving | Prompt Mapping / Tool Mapping | Description
DC5.1 | NTSWSK-12274, | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - Analysis & Design | XLPT_0007 | 20 | 15 | 80% | 0.2 | 4.8 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12275, | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - Code Changes | XLPT_0007 | 50 | 20 | 80% | 7.2 | 42.8 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12276, | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - UAT Validation | XLPT_0007 | 30 | 20 | 80% | 0.8 | 29.2 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12278 | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes -Ofshore Dev/SIT environment testing | XLPT_0007 | 30 | 20 | 80% | 0.8 | 29.2 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12400, | RANSP-xPT: F-20002: Unit testing setup in Feature branch of MUI | XLPT_0002 | 20 | 10 | 62.5% | 0.625 | 19.375 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12401, | RANSP-xPT: F-20002: Unit Test cases for Adhoc file | XLPT_0002 | 50 | 20 | 62.5% | 5.625 | 44.375 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12402, | RANSP-xPT: F-20002: Unit Test Cases for adhocContainer,AdhocHead,AdhocTable,AdhocTableContainer | XLPT_0002 | 30 | 15 | 62.5% | 1.4062 | 28.5938 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12404, | RANSP-xPT: F-20002: Unit Test Cases for Clpt form | XLPT_0002 | 30 | 15 | 62.5% | 1.4062 | 28.5938 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12407, | RANSP-xPT: F-20002: Unit Test cases for KpiModal,Nfilter,perfToolDropdown,ShowFormula.ShowFreq | XLPT_0002 | 30 | 15 | 62.5% | 1.4062 | 28.5938 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12409, | RANSP-xPT: F-20002: Unit Test cases for Button Componenet,CheckBox,DateComponent,Dropdown | XLPT_0002 | 20 | 18 | 62.5% | 0.025 | 19.975 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12410, | RANSP-xPT: F-20002: Unit Test cases for FormPopupMessage,MessageBox,HighTrafficScheduleMessage | XLPT_0002 | 20 | 18 | 62.5% | 0.025 | 19.975 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12411, | RANSP-xPT: F-20002: Unit Test cases for PopupMessage,reportSchedulerCreate,ReportSchedulerList | XLPT_0002 | 30 | 14 | 62.5% | 1.6 | 28.4 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-12412, | RANSP-xPT: F-20002: Unit Test cases for ReportSchedulerPage,ReportSubmittedMessage | XLPT_0002 | 20 | 15 | 62.5% | 0.15625 | 19.8438 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11539, | RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization -Patch Preparation For 5G | XLPT_0006 | 30 | 4 | 70% | 4.732 | 25.268 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11540, | RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization-MOP Preparation For 5G | XLPT_0006 | 20 | 4 | 70% | 1.792 | 18.208 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11542 | RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization- Code Review | XLPT_0006 | 20 | 10 | 70% | 0.7 | 19.3 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11568, | RANSP-xPT: F-18940: Ingestor Setup related to DB | XLPT_0006 | 20 | 10 | 70% | 0.7 | 19.3 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11569, | RANSP-xPT: F-18940: Extractor Setup related to DB | XLPT_0006 | 20 | 24 | 70% | 0.112 | 19.888 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11546, | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Patch Preparation | XLPT_0006 | 20 | 20 | 70% | 0 | 20 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11547, | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Code and Patch Review | XLPT_0006 | 10 | 8 | 70% | 0.028 | 9.972 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11550 | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- UAT Validation | XLPT_0006 | 10 | 16 | 70% | 0.252 | 9.748 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11574, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Analysis | XLPT_0006 | 20 | 4 | 70% | 1.792 | 18.208 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11575, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Development | XLPT_0006 | 30 | 8 | 70% | 3.388 | 26.612 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11576, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Testing | XLPT_0006 | 20 | 8 | 70% | 1.008 | 18.992 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11592, | RANSP-xPT: F-18952: Analyze the code changes and identify if any dependent changes for ALPT,ELPT and PT5G | XLPT_0008 | 30 | 20 | 90% | 0.9 | 29.1 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-11600, | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Analysis | XLPT_0008 | 20 | 20 | 90% | 0 | 20 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-10562, | RANSP-xPT:F-15709: Filtering - Script to pull the KPI from raw files (Ericsson) Description - Python script to pull the counters and load them to R tables. | XLPT_0007 | 50 | 8 | 80% | 14.112 | 35.888 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-10555, | RANSP-xPT: F-15710 Analysis - Report engine memory reduction Description - Analyse the possible scope in report engine that is consuming memory with the intent of speeding up the engine. (Thread profiling etc.,) | XLPT_0008 | 50 | 4 | 90% | 19.044 | 30.956 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-10559, | RANSP-xPT: F-15711: Analysis - Report engine work load management Description - When report generation is triggered from UI manage the load such that the report engine doesn't slow down or crashes | XLPT_0008 | 50 | 4 | 90% | 19.044 | 30.956 | No prompt templates available. But we have reusable code
DC5.1 |  | Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 CUUP Enable Development and Load data -SIT | XLPT_0004 | 10 | 8 | 62.5% | 0.025 | 9.975 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-9365, | Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 - MOP creation | XLPT_0004 | 10 | 8 | 62.5% | 0.025 | 9.975 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-9366 | Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 -Parser and Loader Readiness-UAT | XLPT_0004 | 10 | 20 | 62.5% | 0.625 | 9.375 | No prompt templates available. But we have reusable code
DC5.1 |  | RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - CUUP Enable Development and Load data -SIT | XLPT_0004 | 10 | 20 | 62.5% | 0.625 | 9.375 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-9648 | RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 -Parser and Loader Readiness-UAT | XLPT_0004 | 10 | 16 | 62.5% | 0.225 | 9.775 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-10023, | RANSP-xPT: F-15689: Bulk Formula Update - Analysis | XLPT_0008 | 50 | 8 | 90% | 15.876 | 34.124 | No prompt templates available. But we have reusable code
DC5.1 | NTSWSK-10025, | RANSP-xPT: F-15689: Bulk Formula Update - MS Changes for Template Download | XLPT_0003 | 50 | 4 | 65% | 13.754 | 36.246 | No prompt templates available. But we have reusable code
DC5.1 | F-20008 | RANSP-xPT: F-20008 Crontab Versioning - Gather the multiple server cron data from Prod server | XLPT_0009 | 30
DC5.1 | F-20008 | RANSP-xPT: F-20008-Crontab Versioning - Run and validate the prod pipeline with collective server | XLPT_0009 | 30
DC5.1 | F-19998 | RANSP-xPT: F-19998: Verify Login Logout | XLPT_0005 | 10
DC5.1 | F-19998 | RANSP-xPT: F-19998: Verify report builder report | XLPT_0005 | 30
DC5.1 | F-19998 | RANSP-xPT: F-19998: Verify Structured Adhoc report | XLPT_0005 | 30
DC5.1 | F-19998 | RANSP-xPT: F-19998: Verify VSWR report SAH in Ericsson 4G | XLPT_0005 | 10
DC5.2 | NTSWSK-11551, | RANSP-xPT: F-18930: 5g WebSVC GET to POST- Regression SIT |  | 30
DC5.2 | NTSWSK-11559, | RANSP-xPT: F-18930: 4g WebSVC GET to POST- Regression SIT |  | 30
DC5.2 | NTSWSK-11560, | RANSP-xPT: F-18934: Create a deployment YAML for UAT and deploy |  | 20
DC5.2 | NTSWSK-11561, | RANSP-xPT: F-18934: - UAT Validation - Test the POST Controller against the existing GET controller response |  | 20
DC5.2 | NTSWSK-11562, | RANSP-xPT: F-18934: - Create the MOP for the 4g WebSVC GET to POST deployment |  | 10
DC5.2 | NTSWSK-11563, | RANSP-xPT: F-18934: - Production Deployment - 4g WebSVC GET to POST - Tracker |  | 10
DC5.2 | NTSWSK-11564 | RANSP-xPT: F-18934: Regression testing |  | 20
DC5.2 | NTSWSK-11311 | RANSP-xPT: F-18907: Ericsson 5G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) |  | 20
DC5.2 | NTSWSK-11362 | RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - Development (Parser , Loader Development&DBA Validation) |  | 20
DC5.2 | NTSWSK-12403, | RANSP-xPT: F-20002: Unit Test Cases for Alpt form |  | 30
DC5.2 | NTSWSK-12405, | RANSP-xPT: F-20002: Unit Test Cases for Dropdown file |  | 50
DC5.2 | NTSWSK-12408, | RANSP-xPT: F-20002: Unit Test cases for thresholdEntry, thresholdGroup, thresholdHelp,thresholdModal |  | 30
DC5.2 | NTSWSK-12413, | RANSP-xPT: F-20002: Unit Test cases for ReportActions |  | 20
DC5.2 | NTSWSK-12414 | RANSP-xPT: F-20002: Unit Test cases for ReportReducers |  | 20
DC5.2 | NTSWSK-11532, | RANSP-xPT: F-18921: Identify all the samsung Relates table |  | 20
DC5.2 | NTSWSK-11533, | RANSP-xPT: F-18921: Prepare patch with Samsung tables and deploy in PT5GX |  | 30
DC5.2 | NTSWSK-11570, | RANSP-xPT: F-18940: Create all Required Db artifacts in ALPTX and ALPT_CENTRAL(Table,procedures,Views) |  | 30
DC5.2 | NTSWSK-11571, | RANSP-xPT: F-18940: Load all the required metadata in reporting cluster |  | 20
DC5.2 | NTSWSK-11572, | RANSP-xPT: F-18940: Create required Pipelines |  | 20
DC5.2 | NTSWSK-11548, | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Mop Creation |  | 10
DC5.2 | NTSWSK-11577, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Patch Preparation |  | 10
DC5.2 | NTSWSK-11578, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- UAT Deployment |  | 10
DC5.2 | NTSWSK-11583, | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Analysis |  | 30
DC5.2 | NTSWSK-11584, | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Development |  | 50
DC5.2 | NTSWSK-11585, | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Testing |  | 50
DC5.2 | NTSWSK-11593, | RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Development |  | 30
DC5.2 | NTSWSK-11594, | RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Testing |  | 20
DC5.2 | NTSWSK-11601, | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Development |  | 30
DC5.2 | NTSWSK-11602, | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Testing |  | 20
DC5.2 | NTSWSK-10563, | RANSP-xPT:F-15709: Filter as WASM - Script as plugin for DB - POC Description - WASM script as plugin to directly load the data. |  | 50
DC5.2 | NTSWSK-10556, | RANSP-xPT: F-15710 POC for memory reduction & speeding up reports based on analysis |  | 30
DC5.2 | NTSWSK-10560, | RANSP-xPT: F-15711: POC for handling huge and multiple reports based on analysis |  | 30
DC5.2 | NTSWSK-10240, | RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decoder - 24Q2 - MOP creation-UAT |  | 10
DC5.2 | NTSWSK-10243 | RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decode- 24Q2 -Parser and Loader Readiness-UAT |  | 10
DC5.2 | NTSWSK-9645, | RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 - MOP creation- |  | 10
DC5.2 | NTSWSK-9635, | RANSP-xPT: F-15592: Corining 4G 24.4 - - MOP creation- |  | 10
DC5.2 | NTSWSK-10089 | RANSP-xPT: F-15592: Corining 4G 24.4 --RF Validation-UAT |  | 10
DC5.2 | NTSWSK-9637 | RANSP-xPT: F-15592: Corining 4G 24.4 --Parser and Loader Readiness-UAT |  | 10
DC5.2 | NTSWSK-10098 | RANSP-xPT: F-15593: Corining 5G 24.4 --RF Validation-SIT |  | 30
DC5.2 | NTSWSK-9641, | RANSP-xPT: F-15593: Corining 5G 24.4 - - MOP creation-UAT |  | 10
DC5.2 | NTSWSK-9536 | RANSP-xPT: F-15593: Corining 5G 24.4 --RF Validation-UAT |  | 30
DC5.2 | NTSWSK-9643 | RANSP-xPT: F-15593: Corining 5G 24.4 --Parser and Loader Readiness-UAT |  | 10
DC5.2 | F-19998 | RANSP-xPT: F-19998: Verify Specail KPI Traffic should not be zero or negative |  | 20
DC5.2 | F-19998 | RANSP-xPT: F-19998: Verify Export file csv and excel |  | 20
DC5.2 | F-19998 | RANSP-xPT: F-19998: Verify Content getting loaded after report selection is made in SAH Page |  | 10
DC5.2 | NTSWSK-10024, | RANSP-xPT: F-15689: Bulk Formula Update - UI Changes |  | 50
DC5.2 | NTSWSK-10026, | RANSP-xPT: F-15689: Bulk Formula Update - MS changes on formula submission |  | 80
DC5.2 | F-20008 | RANSP-xPT: F-20008-Parser versioning - Analysis the prod structure for pipeline design |  | 20
DC5.2 | F-20008 | RANSP-xPT: F-20008-Parser versioning - Create a master structure based on Parser region, vendor and server |  | 20
DC-5.3 | NTSWSK-11354 | RANSP-xPT: F-18909: Ericsson 4G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) |  | 20
DC-5.3 |  | Ericsson EBSN 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) |  | 20
DC-5.3 | NTSWSK-12406, | RANSP-xPT: F-20002: Unit Test cases for EnodebMenu, FilterAccordian,FilterMultiSelect |  | 80
DC-5.3 | NTSWSK-11534, | RANSP-xPT: F-18921: Indentify Erricssion tables |  | 20
DC-5.3 | NTSWSK-11535, | RANSP-xPT: F-18921: Prepare patch for Erricssion Table and deploy in PT5GX |  | 30
DC-5.3 | NTSWSK-11536 | RANSP-xPT: F-18921: Make required Artifacts changes in Reporting Side for schema Xlpt |  | 50
DC-5.3 | NTSWSK-11573 | RANSP-xPT: F-18940: Test with some sample data for all the Nodes(ENODEB,MME,PGW and SGW) |  | 30
DC-5.3 | NTSWSK-11549, | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Prod Deployment |  | 10
DC-5.3 | NTSWSK-11579, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- UAT Validation |  | 10
DC-5.3 | NTSWSK-11580, | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Mop Creation |  | 10
DC-5.3 | NTSWSK-11586 | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Patch Preparation |  | 20
DC-5.3 | NTSWSK-11595 | RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Patch Preparation |  | 20
DC-5.3 | NTSWSK-11603 | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Patch Preparation |  | 10
DC-5.3 | NTSWSK-10564 | RANSP-xPT:F-15709: KPI calculation engine refactoring - to reduce memory usage and remove queuing |  | 50
DC-5.3 | NTSWSK-10557 | RANSP-xPT: F-15710:LLD creation for memory reduction analysis |  | 30
DC-5.3 | NTSWSK-10561 | RANSP-xPT: F-15711: LLD creation for work load management analysis |  | 30
DC-5.3 | NTSWSK-9951 | RANSP-xPT:F-15667: RF validation for structured adhoc page Regression |  | 20
DC-5.3 | NTSWSK-9952 | RANSP-xPT:F-15667: RF validation for Report Builder page Regression |  | 20
DC-5.3 | NTSWSK-9953 | RANSP-xPT:F-15667: RF validation for Login, Formula Editor and Report schedular page Regression |  | 10
DC-5.3 | NTSWSK-9955 | RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - Sasmung_4G_5G |  | 30
DC-5.3 | NTSWSK-9957 | RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - SPC_4G_5G |  | 30
DC-5.3 | F-19998 | RANSP-xPT: F-19998: Verify ARFCN range filder |  | 20
DC-5.3 | F-19998 | RANSP-xPT: F-19998: Verify Middle digit ARFCN filter |  | 20
DC-5.3 | F-19998 | RANSP-xPT: F-19998: Vefify ARFCN band filter |  | 20
DC-5.3 | NTSWSK-10055, | RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders- Samsung |  | 20
DC-5.3 | NTSWSK-10056, | RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Corning |  | 20
DC-5.3 | NTSWSK-10057, | RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Core 5GC |  | 10
DC-5.3 | NTSWSK-10058, | RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Core EPC |  | 20
DC-5.3 | NTSWSK-10059, | RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Cisco and epdg |  | 10
DC-5.3 | NTSWSK-10027, | RANSP-xPT: F-15689: Bulk Formula Update - MS Unit Test Case changes on formula submission |  | 20
DC-5.3 | NTSWSK-10028, | RANSP-xPT: F-15689: Bulk Formula Update Dev and SIT deployment - UI Integration |  | 30
DC-5.3 | NTSWSK-10029, | RANSP-xPT: F-15689: Bulk Formula Update Dev and SIT deployment - Regression testing |  | 20
DC-5.3 | F-20008 | RANSP-xPT: F-20008Parser versioning - Create a pipeline script for the prod parser config |  | 30
DC-5.3 | F-20008 | RANSP-xPT: F-20008-Parser versioning - Validate the Prod env pipeline - intiate from UAT |  | 30

## Additional Observations
S.No | Type | Observation