## DC-4
Project | Sub Project | DC/Quater | Sprint | Activity | SDLC | AI Tool | Type of Work | Tech Stack | Feature/JIRA | Develper | Onshore/Offshore | Accuracy | Efficiency | Effort without AI(SPs) | Effort with AI(SPs) | Issues/Challenges/Remark | Prompt Used
XPT | RAN2 | DC4 | DC 4 | Bash Loop enhancement | Automation | gemini | New | Bash | NTSWSK-9661 | Raiyan | Offshore | 70% | 30% | 3 | 2.5
XPT | RAN2 | DC4 | DC 4 | Code generation | Development | Gemini | New | Python | NTSWSK-9633 | 1 | Offshore | 75% | 60% | 2 | 1.5 | Helped in python script generation with good amount of inputs.
XPT | CORE | DC4 | DC4 | Errors found in run time/compilation | Development | Gemini | New | MEMSQL,Shell script,Unix commands |  |  | Offshore | 50% | 50% | 3 | 2.2 | It doesnt give response accurately in initial. We need to try out multiple input and it gives correct results for direct questions
XPT | RAN2 | DC4 | DC 4.2 | Development | Development | Gemini | New | Python | NTSWSK-9633 | 1 | Offshore | 100% | 80% | 2 | 1 | Helped in accelerating the process and complete the story quickly
XPT | RAN2 | DC4 | DC 4.2 | Testing(Build issue) | Testing | Gemini | New | Cypress | NTSWSK-11505 | 1 | Offshore | 40% | 50% | 2 | 1.5 | Helped in finding root cause which helped in proceeding the task clearly
XPT | RAN2 | DC4 | DC 4.2 | Development | Development | Gemini | New | Java | NTSWSK-10125 | 1 | Offshore | 100% | 10% | 8 | 7 | Refactoring a few code changes using Gemeni AI
XPT | RAN1 | DC4 | DC 4.2 | Unit testcases | Development | Gemini | New | Java | NTSWSK-10127 | 1 | Offshore | 100% | 20% | 2 | 1.6 | Prepared some mock data according to the source code,test cases here found a few issues during a running test cases and fixed a those issues using GEN AI
XPT | RAN2 | DC4 | DC 4.3 | Bug Fixes | Development | Gemini | New | Java | NTSWSK-11829 | 1 | Offshore | 100% | 20% | 1 | 0.7 | Using this AI , found data validation issue from data base side
XPT | RAN1 | DC4 | DC 4.1 | Unit testcases | Development | Gemini | New | Java | NTSWSK-9791 | 1 | Offshore | 100% | 5% | 2 | 1.7 | Fixed a some runtime exceptions when running a testcases
XPT | RAN1 | DC4 | DC 4.2 | Unit testcases | Development | Gemini | New | Java | NTSWSK-9923 | 1 | Offshore | 100% | 7% | 2 | 1.6 | Fixed a some runtime exceptions when running a testcases
XPT | RAN2 | DC4 | DC 4.1 | Performance Bugfixes | Development | Gemini | New | JavaScript | NTSWSK-9931 | shashikiran | Offshore | 30% | 50% | 5 | 4.5 | Refactoring a few code
XPT | RAN2 | DC4 | DC 4.2 | Performance Bugfixes | Development | Gemini | New | JavaScript | NTSWSK-9933 | shashikiran | Offshore | 30% | 50% | 3 | 2.5 | Refactoring a few code
XPT | RAN2 | DC4 | DC 4.2 | Performance | Development | Gemini | New | JavaScript | NTSWSK-9934 | shashikiran | Offshore | 50% | 30% | 5 | 4.5 | Refactoring a few code
XPT | RAN2 | DC4 | DC 4.3 | Performance | Development | Gemini | New | JavaScript | NTSWSK-9935 | shashikiran | Offshore | 40% | 0% | 8 | 7.8 | Using LightHouse to check areas of improvisation in the application with those points used GEMINI
XPT | RAN2 | DC4 | DC 4.2 | Enhancement | Development | Gemini | New | Python
XPT | RAN2 | DC3 | DC 3.2 | Installation | Development | Gemini | New | Python | NTSCA-36896 | 1 | Offshore | 60% | 30% | 2 | 3 | Helped in installation and configuration steps
XPT | RAN2 | DC4 | DC 4.2 | Code Review | Review | Gemini | New | MEMSQL,Shell script,Unix commands | NTSCA-36896 | 1 | Offshore | 5% | 5% | 1 | 1 | Startdards are not as per our Code standards
XPT | RAN2 | DC4 | DC 4.2 | Patch Preparation and UAT Deplyment | Deployment,Review | Gemini | New | MEMSQL,Shell script,Unix commands | INC013554065 |  | Offshore | 0% | 0% | 1 | 1.1 | Not useful for Deployments and Preparing Patch
XPT | RAN2 | DC4 | DC 4.2 | Cron ID generate | Automation | Gemini | New | Linux | NTSWSK-9666 | Raiyan | Offshore | 100% | 80% | 3 | 2.8 | Uinque ID for list cron job
XPT | RAN2 | DC4 | DC 4.3 | For Script validation | Automation | Gemini | New | Bash | NTSWSK-9668 | Raiyan |  | 70% | 50% | 3 | 3
XLPT | RAN2 | DC4 | CD 4.3 | Code genration | Development | Gemini | Development | Java | NTSWSK-10556 | Praveen | offshore | 60% | 30% | 3 | 2.8

## DC-5
Project | Sub Project | DC/Quater | Sprint | Activity | SDLC | AI Tool | Type of Work | Tech Stack | Feature/JIRA | Develper | Onshore/Offshore | Accuracy | Efficiency | Effort without AI(SPs) | Effort with AI(SPs) | Efforts Saving (Sp's) | Issues/Challenges/Remark | Prompt Used
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12400, | Shashikiran | Offshore | 50% | 25% | 2 | 1.8 | 0.2 | as per our Project code base its not giving the proper code here we need to tweek it
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12409, | Shashikiran | Offshore | 80% | 80% | 2 | 1..5 | 0.5 | setState is and Few methods it not getting covered | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12410, | Shashikiran | Offshore | 100% | 85% | 2 |  |  |  | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12411, | Shashikiran | Offshore | 70% | 70% | 3 |  |  |  | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12412, | Shashikiran | Offshore |  |  | 2 |  |  |  | Gems attached in G-Drive
XPT |  | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12404, | Manju | Offshore | 70% | 30% | 3 | 2 |  | Since AI doesnt have idea in regard with local configuration configuration, There is no much accuracy. Co-Pilot may fill this gap | Gems attached in G-Drive
XPT |  | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12407, | Manju | Offshore | 70% | 50% | 3 | 2 |  | Got the errors , Can be resolved when gone through whole component . Debugging efforts to get the dummy test data related tp props, state despite the use of AI | Gems attached in G-Drive
XPT |  | DC5 | DC5.1 | Test cases | Testing | gemini |  | MemSQL | NTSWSK-11550 | Priya | Offshore | 50% | 40% | 1 | 1 |  | Got the test case for a SP to be tested
XPT |  | DC5 | DC5.1 | Documantation | Design | gemini | New | Java | NTSWSK-12274, | Praveen | Offshore | 70% | 80% | 2 | 1.5 | 0.5 | As per given requrement it generated on my given inputs in propessional way
XPT |  | DC5 | DC5.1 | Code Optimazation | Development | gemini | New | Java | NTSWSK-12275, | Praveen | Offshore | 70% | 50% | 5 | 4 | 1 | Need to debug the code and apply the manually logic in existing code according to our requirement
XPT |  | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs | NTSWSK-12401 | Gowtham | Offshore | 50% | 25% | 5 | 4 | 1
XPT |  | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs | NTSWSK-12402 | Gowtham | Offshore | 50% | 25% | 3 | 2 | 1
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java | NTSWSK-10559 | AtchuthaSai | Offshore | 50% | 50% | 3 | 2 | 2 | Refactoring code changes and also find out time between old and new code
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java | NTSWSK-10023 | AtchuthaSai | Offshore | 40% | 4% | 3 | 2 | 2 | For this story , with the help of this AI finding some classes and generated excel reports
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | MemSQL | NTSWSK-11600, | Vijay | Offshore | 60% | 50% | 1 | 1 |  | Analysed the existing code using AI
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java and Linux | NTSWSK-8381 | Veera | Offshore | 40% | 30%
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java and Linux | NTSWSK-8387 | Veera | Offshore | 40% | 30%
XPT |  | DC5 | DC5.1 | Code Review | Review | Gemini | New | MemSQL | NTSWSK-11310, | KrishnaReddy | Offshore | 0% | 0% | 1 |  |  | As per our coding and deploymnet Patch process ,Gen AI is not Fesable to provide inputs
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | MemSQL | NTSWSK-11574, | KrishnaReddy | Offshore | 50% | 50% | 2 | 1.5 | 0.5
XPT |  | DC5 | DC-5.2 | Unit testcases | Testing | Gemini | New | Java | RANSP-xPT: F-18930 | Praveen | Offshore | 70% | 60% | 1 | 0.5 | 0.5 | after using genai getting good covered
XPT |  | DC5 | DC-5.2 | Code Developmet | Development | Gemini | New | Java | NTSWSK-11559, | Praveen | Offshore | 60% | 70% | 3 | 2 | 1
XPT |  | DC5 | DC-5.2 | Documentation | Deployment | Gemini | New | Java | NTSWSK-11560, | Praveen | Offshore | 50% | 40% | 2 | 1.5 | 0.5
XPT |  | DC5 | DC-5.2 | Validation | Testing | Gemini | New | Java | NTSWSK-11561, | Praveen | Offshore | 40% | 30% | 2 | 1.5 | 0.5
XPT |  | DC5 | DC-5.2 | Documentation | Deployment | Gemini | New | Java | NTSWSK-11562, | Praveen | Offshore | 40% | 30% | 1 | 1 | 0
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | Suresh | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | Decoder | Deployment | Gemini | Old | Java | NTSWSK-11362 | Praveen | Offshore | 30% | 10% | 2 | 2 | 0
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12278 | BALA | Offshore |  |  | 3
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12405, | shashikiran | Offshore | 80% | 70% | 5 |  |  | if lese condtion and setState methods are not getting covered | DC5/DC5.1/SimpleRTLPrompt
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12408, | Shashikiran | Offshore | 70% | 55% | 3 |  |  | if lese condtion and setState methods are not getting covered | DC5/DC5.1/SimpleRTLPrompt
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12413, | Manju | Offshore | 60% | 75% | 2 | 1.5 | 0.5 | Since AI doesnt have idea in regard with local configuration configuration, There is no much accuracy. Co-Pilot may fill this gap | Gems/RTLGem
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12414 | Manju | Offshore | 60% | 70% | 2 | 1.5 | 0.5 |  | DC5/DC5.1/SimpleRTLPrompt
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-12403 | Manju | Offshore | 55% | 60% | 3 | 2 | 1 | Loops and More lines of code | DC5/DC5.1/SimpleRTLPrompt
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11532, | Vijay | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11533, | Vijay | Offshore |  |  | 3
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11570, | Arun | Offshore |  |  | 3
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11571, | Arun | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11572, | Arun | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11548, | Vijay | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11577, | Priya | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11578, | KrishnaReddy | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11583, | Vijay | Offshore |  |  | 3
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11584, | Priya | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11585, | Vijay | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | Analysis | Analysis | gemini | New | MemSql | NTSWSK-11592, | Priya | Offshore | 60 | 50 | 3 | 2 | 1 |  | I need the specific SQL queries and steps for SingleStore (MemSQL) to analyze changes to a table schema when a new column is added. The output should identify potentially affected views, stored procedures, functions, triggers, and foreign key constraints. For each, provide the SQL query, explain how to interpret the results, and suggest necessary modifications.
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | MemSql | NTSWSK-11593, | Priya | Offshore | 90 | 100 | 3 | 1 | 2 | Using this prompt we updated for seven tables | Please provide the SQL ALTER TABLE ADD COLUMN statement for SingleStore (MemSQL) to add a timestamp column. The new column should have microsecond precision, automatically default to the current timestamp on insertion, and automatically update to the current timestamp whenever the row is modified. Use placeholders for the table name and the new column name
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11594, | Vijay | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11601, | Vijay | Offshore |  |  | 3
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-11602, | Priya | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-10563, | Karthic | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | Java | NTSWSK-10560, | AtchuthaSai | Offshore | 50% | 50% | 3 | 1 | 1 | Calculating some bussiness logics time | How to calculate the time between particular code?
|  | DC5 | DC-5,.2 | Analysis | Development | gemini | New | Java | NTSWSK-10026, | AtchuthaSai | Offshore | 30% | 30% | 8 | 1 | 1 | Generate some bussiness logics code | Implemented some bussiness logics according to requirements
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | Java | NTSWSK-10557 | AtchuthaSai | Offshore | 50% | 50% | 5 | 2 | 2 | Refactoring some bussiness logics | Converting old logics to new logics code
XPT |  | DC5 | DC-5.3 | [5 empty] | NTSWSK-10555, | Karthic | Offshore |  |  | 5
XPT |  | DC5 | DC-5.3 | Analysis | Development | Gemini | New | Java | NTSWSK-10559, | Atchutha | Offshore | 40% | 50% | 5 | 1 | 1 | Analayiss and refactoring bussinesss code
XPT |  | DC5 | DC-5.3 | Analysis | Development | Gemini | New | Java | NTSWSK-10560, | Atchutha | Offshore | 30% | 50% | 3 | 1 | 1 | Possible to coverted old code changes to new version of code changes
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-10240, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-10243 | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-9645, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-9635, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-9637, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-9641, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-9643, | Bala | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | suresh | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | suresh | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | suresh | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | suresh | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | Gowtham | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | Gowtham | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | F-15667 | Gowtham | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-10024, | Gowtham | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | Development | Development | Gemeni | New | Java | NTSWSK-10026, | Sai | Offshore | 20% | 30% | 8 | 1 | 1 | Generating some model classes using AI
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-14279, | Raiyan | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-14280, | Raiyan | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | [6 empty] | Vijay | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [6 empty] | Priya | Offshore |  |  | 1
XPT |  | DC5 | DC-5.2 | [6 empty] | Vijay | Offshore |  |  | 2
XPT |  | DC5 | DC-5.2 | [6 empty] | Vijay | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | [6 empty] | Vijay | Offshore |  |  | 5
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-14279, | Raiyan | Offshore | 50% | 50% | 2
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-14280, | Raiyan | Offshore | 30% | 30% | 5
XPT |  | DC5 | DC-5.2 | [5 empty] | NTSWSK-14284 | Raiyan | Offshore | 50% | 50% | 3
Not worked in 5.2
[9 empty] | NTSWSK-11311 | Manju
[9 empty] | NTSWSK-11354 | Manju
[9 empty] | NTSWSK-11602 | Priya
[9 empty] | NTSWSK-11584 | Priya
DC5.3
XPT |  | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | NTSWSK-11311 | Manju |  | - | - | 2
XPT |  | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | NTSWSK-11354 | Manju |  | - | - | 2
XPT |  | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | Ericsson EBSN 25Q1 | Manju |  | - | - | 2
XPT |  | DC-5 | DC-5.3 | [5 empty] | NTSWSK-12406, | Shashikiran |  | 85% | 80% | 8
XPT |  | DC-5 | DC-5.3
XPT |  | DC-5 | DC-5.3 | [5 empty] | F-15667 | Gowtham |  |  |  | 2
XPT |  | DC-5 | DC-5.3 | [5 empty] | F-15667 | Gowtham |  |  |  | 2
XPT |  | DC-5 | DC-5.3 | [5 empty] | F-15667 | Gowtham |  |  |  | 2
XPT |  | DC-5 | DC-5.3 | Development | Development | Gemeni | New | Java | NTSWSK-10027, | Sai | Offshore | 30% | 20% | 2 | 1 | 1 | Generating mock classes using GI
XPT |  | DC-5 | DC-5.3 | Development | Development | Gemeni | New | Java | NTSWSK-10028, | Sai | Offshore | 50% | 50% | 3 | 1 | 1 | Found testcases using GEN AI
XPT |  | DC-5 | DC-5.3 | [5 empty] | NTSWSK-10029, | Suresh |  |  |  | 2
XPT |  | DC-5 | DC-5.3 | Development | Development | Gemeni | New | Java | NTSWSK-10030 | Sai | Offshore | 50% | 50% | 2 | 1 | 1 | Found unkonwn commands uisng GEN AI
XPT |  | DC-5 | DC-5.3 | [5 empty] | RANSP-xPT: F-20008 | Raiyan |  |  |  | 3
XPT |  | DC-5 | DC-5.3 | [5 empty] | RANSP-xPT: F-20008 | Raiyan |  |  |  | 3
XPT |  | DC-5 | DC-5.3 | Analysis | Development | gemini | New | Java | NTSWSK-10556, | Praveen | Offshore | 60% | 40% | 3 | 2 | 1 | Analyzed the Existing code and idenfied the some bussiness logics who takes more time and also finding the solution | Converting old logics to new logics code
XPT |  | DC-5 | DC-5.3
XPT |  | DC-5 | DC-5.3 | [10 empty] | total:- 36
XPT |  | DC-5 | DC-5.3
XPT |  | DC-5 | DC-5.3 | [5 empty] | NTSWSK-11549, | Vijay |  |  |  | 1
[9 empty] | NTSWSK-11603 | Priya |  |  |  | 1
[9 empty] | NTSWSK-11534, | Priya |  | 70% | 85% | 2
[9 empty] | NTSWSK-11535, | Priya |  | 60% | 70% | 3
[9 empty] | NTSWSK-11586 | KrishnaReddy |  |  |  | 2
[9 empty] | NTSWSK-11579 | KrishnaReddy |  |  |  | 1
[9 empty] | NTSWSK-11580 | KrishnaReddy |  |  |  | 1
[9 empty] | NTSWSK-11536 | KrishnaReddy |  |  |  | 5

## DC-6
Project | Sub Project | DC/Quater | Sprint | Activity | SDLC | AI Tool | Type of Work | Tech Stack | Feature/JIRA | Develper | Onshore/Offshore | Accuracy | Efficiency | Effort without AI(SPs) | Effort with AI(SPs) | Efforts Saving (Sp's) | Issues/Challenges/Remark | Prompt Used
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12400, | Shashikiran | Offshore | 50% | 25% | 2 | 1.8 | 0.2 | as per our Project code base its not giving the proper code here we need to tweek it | /GEMS/RTLGEM
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12409, | Shashikiran | Offshore | 80% | 80% | 2 | 1..5 | 0.5 | setState is and Few methods it not getting covered | /GEMS/RTLGEM
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12410, | Shashikiran | Offshore | 100% | 85% | 2 |  |  |  | Gems attached in G-Drive

## ResourseList
RAN2
Techstack | Name | ORG |  |  | Responsibility
Scrum | K. Nandini Chandravathi | Incedo |  | Hyderabad |  |  |  | Manager
Architect | Arunraja | Incedo | mar8c39 | Chenanni | RAN1, RAN2, CORE |  |  | Architect so no uses his Jira
Fullstack | Karthic Hari Narayanan | Incedo | narak24 | Chenanni | Lead-Backend/UI
Backend/MS | Atchutha Sai | Incedo | srigaat | Chenanni
DB | Gongati Krishna Reddy | Incedo | Krigo75 | Hyderabad | Lead-DB
DB/Backend | Vijaykumar pownraj | Incedo | pownri | Chenanni
DB | L Priyadarshini | Incedo | LPR3BMV | Chenanni |  |  | 11
UI | TP, Shashikiran | Incedo | TPSH | Hyderabad
Backend/MS | Praveen Kumar | Incedo | kumpr46 | Hyderabad
Backend/MS | Chilakala Venkata Manjunadha | Incedo | chilve8 | Hyderabad
UI | Gowtham S | Incedo | sundgo8 | Chenanni
QA | Suresh Kumar Subrahmanian | Incedo | subsu6r | Chenanni
Devops | Mohammed Raiyan | Incedo | raiyamo | Chenanni
RAN1
Techstack | Name | ORG | Responsibility |  | Primary Skill
Scrum | Vinothkumar | Incedo
Backend/MS | Balakrishnan C | Incedo | Lead | Chennai | Java, Springboot, MS |  | 1
CORE1
Techstack | Name | ORG | Responsibility |  | Primary Skill
DB | Shraddha Janawadker | Incedo | DB-Lead | Hyderabad | Oracle,PL/SQL,Memsql
Fullstack | Abhinav Sahai | Incedo |  | Chennai | Java, ,Springboot, MS, |  | 3
Backend/MS | Veeramahendraiah Bale | Incedo | Backend-Lead | Hyderabad | Java, ,Springboot, MS
total count is 13

## Sheet3
praveen
MVP-Feature | Story | Iteration | Story points | Assignee | Story id | Dependency/Affecting on Core (Y/N)
| RANSP-xPT: F-18930: 5g WebSVC GET to POST- Regression SIT | DC5-Sprint 2 | 3 |  | NTSWSK-11551,
Migrate 5G APIs from GET to POST - Phase 2 - UAT, MOP and Prod Deployment | RANSP-xPT: F-18930: Deploy to UAT through pipeline | DC5-Sprint 2 | 2 | Sourav | NTSWSK-11552,
| RANSP-xPT: F-18930: - UAT Validation - Test the POST Controller against the existing GET controller response | DC5-Sprint 3 | 2 | Sourav | NTSWSK-11553,
| RANSP-xPT: F-18930: Create the MOP for the 5g WebSVC GET to POST deployment | DC5-Sprint 3 | 1 | Sourav | NTSWSK-11554,
| RANSP-xPT: F-18930: - Production Deployment - 5g WebSVC GET to POST - Tracker | DC5-Sprint 3 | 1 | Sourav | NTSWSK-11555,
| RANSP-xPT: F-18930: Regression testing | DC5-Sprint 2 | 2 | Sourav | NTSWSK-11556
| RANSP-xPT: F-18930: 4g WebSVC GET to POST- Regression SIT | DC5-Sprint 2 | 3 | Praveen | NTSWSK-11559,
Migrate 4G APIs from GET to POST - Phase 2 - UAT, MOP and Prod Deployment | RANSP-xPT: F-18934: Create a deployment YAML for UAT and deploy | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11560,
| RANSP-xPT: F-18934: - UAT Validation - Test the POST Controller against the existing GET controller response | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11561,
| RANSP-xPT: F-18934: - Create the MOP for the 4g WebSVC GET to POST deployment | DC5-Sprint 2 | 1 | Praveen | NTSWSK-11562,
| RANSP-xPT: F-18934: - Production Deployment - 4g WebSVC GET to POST - Tracker | DC5-Sprint 2 | 1 | Praveen | NTSWSK-11563,
| RANSP-xPT: F-18934: Regression testing | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11564
RANSP-xPT: F-18907: Ericsson 5G 25Q1 decoder - Development, SIT Testing | RANSP-xPT: F-18907: Ericsson 5G 25Q1 Decoder - RF validation-Offshore | DC5-Sprint 3 | 3 | Ben | NTSWSK-11309,
| RANSP-xPT: F-18907: Ericsson 5G 25Q1 Decoder - Code review | DC5-Sprint 2 | 1 | Krishna | NTSWSK-11310,
| RANSP-xPT: F-18907: Ericsson 5G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 2 | 2 | Manju | NTSWSK-11311
RANSP-xPT: Ericsson 4G 25Q1 decoder - Specs, Development, SIT testing | RANSP-xPT: F-18909: Ericsson 4G 25Q1 Decoder - Specifcation | DC5-Sprint 2 | 8 | Karthik kumar | NTSWSK-11351,
| RANSP-xPT: F-18909: Ericsson 4G 25Q1 Decoder - RF validation-Offshore | DC5-Sprint 3 | 3 | Karthik kumar | NTSWSK-11352,
| RANSP-xPT: F-18909: Ericsson 4G 25Q1 Decoder - Code review | DC5-Sprint 3 | 1 | Krishna | NTSWSK-11353,
| RANSP-xPT: F-18909: Ericsson 4G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 3 | 2 | Manju | NTSWSK-11354
RANSP-xPT: Ericsson EBSN 24Q4 decoder - Specs, Development, tetsing | RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - Specifcation | DC5-Sprint 1 | 8 | Ben | NTSWSK-11359,
| RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - RF validation-Offshore | DC5-Sprint 3 | 3 | Karthik kumar | NTSWSK-11360,
| RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - Code review | DC5-Sprint 2 | 1 | Krishna | NTSWSK-11361,
| RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11362
| Ericsson EBSN 25Q1 Decoder - Specifcation |  | 8 | Ben
| Ericsson EBSN 25Q1 Decoder - Code review | DC5-Sprint 3 | 1 | Krishna
| Ericsson EBSN 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 3 | 2 | Manju
RANSP-xPT: Corning 5G 25.2 decoder - Specs | RANSP-xPT: F-18915: Corning 5G 25.2 Decoder - Specifcation |  | 8 | Anandh S | NTSWSK-11512
RANSP-xPT: Corning 4G 25.2 decoder - Specs | RANSP-xPT: F-18917: Corning 4G 25.2 Decoder - Specifcation |  | 8 | Anandh S | NTSWSK-11513
Subscription Service APP_ACTIVITIES_LOG query changes | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - Analysis & Design | DC5-Sprint 1 | 2 | Praveen | NTSWSK-12274,
| RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - Code Changes | DC5-Sprint 1 | 5 | Praveen | NTSWSK-12275,
| RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - UAT Validation | DC5-Sprint 1 | 3 | Praveen | NTSWSK-12276,
| RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes - Prod validation | DC5-Sprint 1 | 3 | Rajender | NTSWSK-12277,
| RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes -Ofshore Dev/SIT environment testing | DC5-Sprint 1 | 3 | Praveen | NTSWSK-12278
RANSp-xPT: MUI Migration - unit testing- Setup and Structure adhoc | RANSP-xPT: F-20002: Unit testing setup in Feature branch of MUI | DC5-Sprint 1 | 2 | Shashikiran | NTSWSK-12400,
| RANSP-xPT: F-20002: Unit Test cases for Adhoc file | DC5-Sprint 1 | 5 | Gowtham | NTSWSK-12401,
| RANSP-xPT: F-20002: Unit Test Cases for adhocContainer,AdhocHead,AdhocTable,AdhocTableContainer | DC5-Sprint 1 | 3 | Gowtham | NTSWSK-12402,
| RANSP-xPT: F-20002: Unit Test Cases for Alpt form | DC5-Sprint 2 | 3 | Manju | NTSWSK-12403,
| RANSP-xPT: F-20002: Unit Test Cases for Clpt form | DC5-Sprint 1 | 3 | Manju | NTSWSK-12404,
| RANSP-xPT: F-20002: Unit Test Cases for Dropdown file | DC5-Sprint 2 | 5 | shashikiran | NTSWSK-12405,
| RANSP-xPT: F-20002: Unit Test cases for EnodebMenu, FilterAccordian,FilterMultiSelect | DC5-Sprint 3 | 8 | Shashikiran | NTSWSK-12406,
| RANSP-xPT: F-20002: Unit Test cases for KpiModal,Nfilter,perfToolDropdown,ShowFormula.ShowFreq | DC5-Sprint 1 | 3 | Manju | NTSWSK-12407,
| RANSP-xPT: F-20002: Unit Test cases for thresholdEntry, thresholdGroup, thresholdHelp,thresholdModal | DC5-Sprint 2 | 3 | Shashikiran | NTSWSK-12408,
| RANSP-xPT: F-20002: Unit Test cases for Button Componenet,CheckBox,DateComponent,Dropdown | DC5-Sprint 1 | 2 | Shashikiran | NTSWSK-12409,
| RANSP-xPT: F-20002: Unit Test cases for FormPopupMessage,MessageBox,HighTrafficScheduleMessage | DC5-Sprint 1 | 2 | Shashikiran | NTSWSK-12410,
| RANSP-xPT: F-20002: Unit Test cases for PopupMessage,reportSchedulerCreate,ReportSchedulerList | DC5-Sprint 1 | 3 | Shashikiran | NTSWSK-12411,
| RANSP-xPT: F-20002: Unit Test cases for ReportSchedulerPage,ReportSubmittedMessage | DC5-Sprint 1 | 2 | Shashikiran | NTSWSK-12412,
| RANSP-xPT: F-20002: Unit Test cases for ReportActions | DC5-Sprint 2 | 2 | Manju | NTSWSK-12413,
| RANSP-xPT: F-20002: Unit Test cases for ReportReducers | DC5-Sprint 2 | 2 | Manju | NTSWSK-12414
RANSp-xPT: MUI Migration - unit testing - Report browser and report builder | RANSP-xPT: F-20004: Unit Test cases for BrowserReports,Filters,LinkFormatter,ReportBrowser,ReportBrowserContainer | DC5-Sprint 1 | 5 | Kajal | NTSWSK-12255,
| RANSP-xPT: F-20004: Unit Test cases for ReportTable,UserTree | DC5-Sprint 1 | 5 | Kajal | NTSWSK-12256,
| RANSP-xPT: F-20004: Unit Test cases for CreateEditTable,DeleteTable | DC5-Sprint 2 | 3 | Kajal | NTSWSK-12257,
| RANSP-xPT: F-20004: Unit Test cases for ReportBuilder,ReportBuilderContainer | DC5-Sprint 3 | 8 | Kajal | NTSWSK-12258,
| RANSP-xPT: F-20004: Unit Test cases for ReportBuilderFormElems | DC5-Sprint 2 | 3 | Kajal | NTSWSK-12259,
| RANSP-xPT: F-20004: Unit Test cases for ReportCreateForm,ReportCreateHead | DC5-Sprint 1 | 2 | Pragathi | NTSWSK-12260,
| RANSP-xPT: F-20004: Unit Test cases for ReportCreatePane,ReportDeleteForm,ReportDeletePane | DC5-Sprint 1 | 3 | Pragathi | NTSWSK-12261, | Thanash
| RANSP-xPT: F-20004: Unit Test cases for ReportTable,ReportViewForm,Report ViewHead | DC5-Sprint 2 | 3 | Pragathi | NTSWSK-12262, | Thanash
| RANSP-xPT: F-20004: Unit Test cases for ReportViewPane,ViewTable | DC5-Sprint 2 | 1 | Pragathi | NTSWSK-12263
RANSP-xPT: 5G Dual cluster Reporting Cluster Prepartion - Phase 1 | RANSP-xPT: F-18921: Sepearate Cluster for Reporting Side for Samsung and Erricssion | DC5-Sprint 1 | 3 | KM | NTSWSK-11530, | KM's name is not there in Jira. Need to check with KM
| RANSP-xPT: F-18921: Create all the required Databases for Reporting Side | DC5-Sprint 1 | 2 | KM | NTSWSK-11531, | KM's name is not there in Jira. Need to check with KM
| RANSP-xPT: F-18921: Identify all the samsung Relates table | DC5-Sprint 2 | 2 | Vijay | NTSWSK-11532,
| RANSP-xPT: F-18921: Prepare patch with Samsung tables and deploy in PT5GX | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11533,
| RANSP-xPT: F-18921: Indentify Erricssion tables | DC5-Sprint 3 | 2 | Priya | NTSWSK-11534,
| RANSP-xPT: F-18921: Prepare patch for Erricssion Table and deploy in PT5GX | DC5-Sprint 3 | 3 | Priya | NTSWSK-11535,
| RANSP-xPT: F-18921: Make required Artifacts changes in Reporting Side for schema Xlpt | DC5-Sprint 3 | 5 | KrishnaReddy | NTSWSK-11536
RANSP-xPT: xLPT Extractor Enhancements for S3 Export,Concurrency and Performance Optimization- 5G Prod | RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization -Patch Preparation For 5G | DC5-Sprint 1 | 3 | Priya | NTSWSK-11539,
| RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization-MOP Preparation For 5G | DC5-Sprint 1 | 2 | KrishnaReddy | NTSWSK-11540,
| RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization-PROD Deployment | DC5-Sprint 2 | 1 | KM | NTSWSK-11541, | KM's name is not there in Jira. Need to check with KM
| RANSP-xPT: F-18925: XLPT Extractor Enhancements for S3 Export, Concurrency and Performance Optimization- Code Review | DC5-Sprint 1 | 2 | Vijay | NTSWSK-11542
RANSP-xPT:Setup Reporting Cluster for UAT DB Extractor and Ingestor | RANSP-xPT: F-18940: ALPTX,ALPT_CENTRAL,XLPT DB Creation and Grants | DC5-Sprint 1 | 1 | KM | NTSWSK-11567, | KM's name is not there in Jira. Need to check with KM
| RANSP-xPT: F-18940: Ingestor Setup related to DB | DC5-Sprint 1 | 2 | Arun | NTSWSK-11568,
| RANSP-xPT: F-18940: Extractor Setup related to DB | DC5-Sprint 1 | 2 | Arun | NTSWSK-11569,
| RANSP-xPT: F-18940: Create all Required Db artifacts in ALPTX and ALPT_CENTRAL(Table,procedures,Views) | DC5-Sprint 2 | 3 | Arun | NTSWSK-11570,
| RANSP-xPT: F-18940: Load all the required metadata in reporting cluster | DC5-Sprint 2 | 2 | Arun | NTSWSK-11571,
| RANSP-xPT: F-18940: Create required Pipelines | DC5-Sprint 2 | 2 | Arun | NTSWSK-11572,
| RANSP-xPT: F-18940: Test with some sample data for all the Nodes(ENODEB,MME,PGW and SGW) | DC5-Sprint 3 | 3 | Arun | NTSWSK-11573
RANSP-xPT: F-18927:RANSP-xPT:Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- PROD | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Patch Preparation | DC5-Sprint 1 | 2 | Priya | NTSWSK-11546,
| RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Code and Patch Review | DC5-Sprint 1 | 1 | Vijay | NTSWSK-11547,
| RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Mop Creation | DC5-Sprint 2 | 1 | Vijay | NTSWSK-11548,
| RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Prod Deployment | DC5-Sprint 3 | 1 | Vijay | NTSWSK-11549,
| RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- UAT Validation | DC5-Sprint 1 | 1 | Priya | NTSWSK-11550
RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Analysis | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Analysis | DC5-Sprint 1 | 2 | KrishnaReddy | NTSWSK-11574,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Development | DC5-Sprint 1 | 3 | KrishnaReddy | NTSWSK-11575,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Testing | DC5-Sprint 1 | 2 | Vijay | NTSWSK-11576,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Patch Preparation | DC5-Sprint 2 | 1 | Priya | NTSWSK-11577,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- UAT Deployment | DC5-Sprint 2 | 1 | KrishnaReddy | NTSWSK-11578,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- UAT Validation | DC5-Sprint 3 | 1 | KrishnaReddy | NTSWSK-11579,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Mop Creation | DC5-Sprint 3 | 1 | KrishnaReddy | NTSWSK-11580,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Prod Deployment | DC5-Sprint 3 | 1 | KM | NTSWSK-11581
RANSP-xPT:Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-Analysi,Development,Testing-ELPT and PT5G | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Analysis | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11583,
| RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Development | DC5-Sprint 2 | 5 | Priya | NTSWSK-11584,
| RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Testing | DC5-Sprint 2 | 5 | Vijay | NTSWSK-11585,
| RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Patch Preparation | DC5-Sprint 3 | 2 | KrishnaReddy | NTSWSK-11586
RANSP-xPT:Add Date Modified column for OM_DATA_INTERVAL,DATA_LOAD_INTERVALS,REGION and MARKET Tables for 4G and 5G-Analysis,Development and Testing | RANSP-xPT: F-18952: Analyze the code changes and identify if any dependent changes for ALPT,ELPT and PT5G | DC5-Sprint 1 | 3 | Priya | NTSWSK-11592,
| RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Development | DC5-Sprint 2 | 3 | Priya | NTSWSK-11593,
| RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Testing | DC5-Sprint 2 | 2 | Vijay | NTSWSK-11594,
| RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Patch Preparation | DC5-Sprint 3 | 2 | KrishnaReddy | NTSWSK-11595
RANSP-xPT:SdpProcessDailyDatabyRegion-Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries for ELPT-UAT | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Analysis | DC5-Sprint 1 | 2 | Vijay | NTSWSK-11600,
| RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Development | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11601,
| RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Testing | DC5-Sprint 2 | 2 | Priya | NTSWSK-11602,
| RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Patch Preparation | DC5-Sprint 3 | 1 | Priya | NTSWSK-11603
M-5490 F-15709-RANSP-xPT: Parserless Architecture-Filter and calucation of refactor engine-Analysis and Design- Phase-1 | RANSP-xPT:F-15709: Filtering - Script to pull the KPI from raw files (Ericsson) Description - Python script to pull the counters and load them to R tables. | DC5-Sprint 1 | 5 | Karthic | NTSWSK-10562, | Incedo
| RANSP-xPT:F-15709: Filter as WASM - Script as plugin for DB - POC Description - WASM script as plugin to directly load the data. | DC5-Sprint 2 | 5 | Karthic | NTSWSK-10563, | Incedo
| RANSP-xPT:F-15709: KPI calculation engine refactoring - to reduce memory usage and remove queuing | DC5-Sprint 3 | 5 | Karthic | NTSWSK-10564 | Incedo
M-5488 F-15710-RANSP-xPT: Reporting engine memory reduction-Analysis and Design-Phase-1 | RANSP-xPT: F-15710 Analysis - Report engine memory reduction Description - Analyse the possible scope in report engine that is consuming memory with the intent of speeding up the engine. (Thread profiling etc.,) | DC5-Sprint 1 | 5 | Karthic | NTSWSK-10555, | Incedo
| RANSP-xPT: F-15710 POC for memory reduction & speeding up reports based on analysis | DC5-Sprint 2 | 3 | Praveen | NTSWSK-10556, | Incedo
| RANSP-xPT: F-15710:LLD creation for memory reduction analysis | DC5-Sprint 3 | 3 | Karthic | NTSWSK-10557 | Incedo
M-5488 F-15711-Reporting engine work load management-Analysis and Design-Phase-1 | RANSP-xPT: F-15711: Analysis - Report engine work load management Description - When report generation is triggered from UI manage the load such that the report engine doesn't slow down or crashes | DC5-Sprint 1 | 5 | Atchutha | NTSWSK-10559, | Incedo
| RANSP-xPT: F-15711: POC for handling huge and multiple reports based on analysis | DC5-Sprint 2 | 3 | Atchutha | NTSWSK-10560, | Incedo
| RANSP-xPT: F-15711: LLD creation for work load management analysis | DC5-Sprint 3 | 3 | Karthic | NTSWSK-10561 | Incedo
M-5246 F-15591- RANSP-xPT:5G ERC 24Q4 and vRAN 24.11 Decoder -UAT, MOP and Prod deployment-Phase 2 | RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decoder - 24Q2 Prod deployment | DC5-Sprint 2 | 1 | C-ops | NTSWSK-10239, | 4
| RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decoder - 24Q2 - MOP creation-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-10240,
| RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decoder - 24Q2 -RF Validation-UAT | DC5-Sprint 2 | 3 | Karthik kumar | NTSWSK-10241,
| RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decode- 24Q2 - 24Q2 DBA Readiness-UAT | DC5-Sprint 2 | 1 | Krishna | NTSWSK-10242,
| RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decode- 24Q2 -Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-10243
M-5246 F-15704-RANSP-xPT: Erc EBSN 24Q3 Decoder- Part 3 - Testing, UAT, MOP and Deployment - Phase-2 | Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 CUUP Enable Development and Load data -SIT | DC5-Sprint 1 | 1 | Praveen
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 CUUP Enable Validation -SIT | DC5-Sprint 1 | 2 | Karthik Kumar
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 Prod deployment | DC5-Sprint 1 | 1 | C-ops | NTSWSK-9364,
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 - MOP creation | DC5-Sprint 1 | 1 | Bala | NTSWSK-9365,
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 -RF Validation-UAT | DC5-Sprint 1 | 3 | Karthik Kumar | NTSWSK-9362
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 - 24Q2 DBA Readines-UAT | DC5-Sprint 1 | 1 | Krishna | NTSWSK-9363,
| Erc EBSN 24Q3 Decoder- Part 3 - 24Q3 -Parser and Loader Readiness-UAT | DC5-Sprint 1 | 1 | Bala | NTSWSK-9366
M-5246 F-15706 RANSP-xPT:Erc EBSN 24Q3 Decoder- Part 4 -Testing, UAT, MOP and Deployment - Phase-2 | RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - CUUP Enable Development and Load data -SIT | DC5-Sprint 1 | 1 | Praveen
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - CUUP Enable Validation -SIT | DC5-Sprint 1 | 2 | Ben
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 Prod deployment | DC5-Sprint 2 | 1 | C-ops | NTSWSK-9644,
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 - MOP creation- | DC5-Sprint 2 | 1 | Bala | NTSWSK-9645,
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 -RF Validation-UAT | DC5-Sprint 1 | 3 | Ben | NTSWSK-9646,
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 - 24Q2 DBA Readiness-UAT | DC5-Sprint 1 | 1 | Krishna | NTSWSK-9647,
| RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 -Parser and Loader Readiness-UAT | DC5-Sprint 1 | 1 | Bala | NTSWSK-9648
| RANSP-xPT: F-15592: Corining 4G 24.4 - Prod deployment | DC5-Sprint 2 | 1 | C-ops | NTSWSK-9634,
| RANSP-xPT: F-15592: Corining 4G 24.4 - - MOP creation- | DC5-Sprint 2 | 1 | Bala | NTSWSK-9635,
| RANSP-xPT: F-15592: Corining 4G 24.4 --RF Validation-UAT | DC5-Sprint 2 | 3 | Anandh S | NTSWSK-10089
| RANSP-xPT: F-15592: Corining 4G 24.4 - - DBA Readiness-UAT | DC5-Sprint 2 | 1 | Krishna | NTSWSK-9636,
| RANSP-xPT: F-15592: Corining 4G 24.4 --Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9637
M-5319 F-15593 RANSP-xPT: Corining 5G 24.4 -UAT,MOP and deployment-Phase-2 | RANSP-xPT: F-15593: Corining 5G 24.4 - Prod deployment | DC5-Sprint 2 | 1 | C-ops | NTSWSK-9640,
| RANSP-xPT: F-15593: Corining 5G 24.4 --RF Validation-SIT | DC5-Sprint 2 | 3 | Anandh S | NTSWSK-10098
| RANSP-xPT: F-15593: Corining 5G 24.4 - - MOP creation-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9641,
| RANSP-xPT: F-15593: Corining 5G 24.4 --RF Validation-UAT | DC5-Sprint 2 | 3 | Anandh S | NTSWSK-9536
| RANSP-xPT: F-15593: Corining 5G 24.4 - - DBA Readiness-UAT | DC5-Sprint 2 | 1 | Krishna | NTSWSK-9642,
| RANSP-xPT: F-15593: Corining 5G 24.4 --Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9643
| RANSP-xPT:F-15667: RF validation for structured adhoc page Regression | DC5-Sprint 3 | 2 | Santha | NTSWSK-9951 | Vz
| RANSP-xPT:F-15667: RF validation for Report Builder page Regression | DC5-Sprint 3 | 2 | Santha | NTSWSK-9952 | Vz
| RANSP-xPT:F-15667: RF validation for Login, Formula Editor and Report schedular page Regression | DC5-Sprint 3 | 1 | Santha | NTSWSK-9953 | Vz
| RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - Nokia_4G_5G | DC5-Sprint 3 | 3 | Karthik kumar | NTSWSK-9954 | TCS
| RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - Sasmung_4G_5G | DC5-Sprint 3 | 3 | Anand R | NTSWSK-9955 | Vz
| RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - Erc_4G_5G | DC5-Sprint 3 | 3 | Ben | NTSWSK-9956 | TCS
| RANSP-xPT:F-15667: RF Validation for RAN Regression Scenarioes - UAT / Production - SPC_4G_5G | DC5-Sprint 3 | 3 | Anandh S | NTSWSK-9957 | Vz
RANSp-xPT: Regression test cases to be modified for MUI for RAN and Cross Vendor - Development & Testing | RANSP-xPT: F-19998: Verify Login Logout |  | 1 | suresh
| RANSP-xPT: F-19998: Verify report builder report |  | 3 | suresh
| RANSP-xPT: F-19998: Verify Structured Adhoc report |  | 3 | suresh
| RANSP-xPT: F-19998: Verify VSWR report SAH in Ericsson 4G |  | 1 | suresh
| RANSP-xPT: F-19998: Verify one market selection should not give multiple markets SAH - report level: market, report type: hourly |  | 2 | suresh
| RANSP-xPT: F-19998: Verify one market selection should not give multiple markets Report Builder - report level: market, report type: hourly |  | 2 | suresh
| RANSP-xPT: F-19998: Verify Threshold filter check |  | 2 | suresh
| RANSP-xPT: F-19998: Verify Cell group upload csv file check |  | 2 | suresh
| RANSP-xPT: F-19998: Verify Cell group report |  | 2 | suresh
| RANSP-xPT: F-19998: Verify Switching between difference vendors in adhoc and report builder page |  | 1 | suresh
| RANSP-xPT: F-19998: Verify BH report |  | 2 | suresh
| RANSP-xPT: F-19998: Verify new formula creation |  | 2 | suresh
| RANSP-xPT: F-19998: Verify Specail KPI Traffic should not be zero or negative | DC5-Sprint 2 | 2 | Gowtham
| RANSP-xPT: F-19998: Verify Export file csv and excel | DC5-Sprint 2 | 2 | Gowtham
| RANSP-xPT: F-19998: Verify Content getting loaded after report selection is made in SAH Page | DC5-Sprint 2 | 1 | Gowtham
| RANSP-xPT: F-19998: Verify ARFCN range filder | DC5-Sprint 3 | 2 | Gowtham
| RANSP-xPT: F-19998: Verify Middle digit ARFCN filter | DC5-Sprint 3 | 2 | Gowtham
| RANSP-xPT: F-19998: Vefify ARFCN band filter | DC5-Sprint 3 | 2 | Gowtham
RANSP-xPTL Loader enhancement to add hints in the control file-Analysis, Design, POC | RANSP-xPT: F-20052: Loader enhancement to add hints in the control file-Analysis | DC5-Sprint 1 | 5 | Pavan | NTSWSK-12252,
| RANSP-xPT: F-20052: Loader enhancement to add hints in the control file-POC | DC5-Sprint 2 | 5 | Pavan | NTSWSK-12253
| RANSP-xPT: F-15666: ELPT - Enable Logical replication Extractor for ELPT | DC5-Sprint 1 | 5 | ANkit | NTSWSK-10048, | TCS
| RANSP-xPT: F-15666: ELPT -Enable Logical replication - S3 Buckets Creation | DC5-Sprint 1 | 5 | Rajender | NTSWSK-10049, | SOW
| RANSP-xPT: F-15666: ELPT - Enable Logical replication - Eanble memsql Pipelines for all tables | DC5-Sprint 1 | 5 | KM | NTSWSK-10050,
| RANSP-xPT: F-15666: ELPT - Enable Logical replication - Validate Loading cluster data is syncing with Reporting cluster | DC5-Sprint 1 | 3 | Pavan | NTSWSK-10051, | Vz
| RANSP-xPT: F-15666: ELPT - Validate MS with Reporting clsuter | DC5-Sprint 1 | 5 | Sourav | NTSWSK-10052, | Vz
| RANSP-xPT: F-15666: ALPT - Enable Logical replication Extractor for ELPT | DC5-Sprint 2 | 5 | ANkit | NTSWSK-10060, | TCS
| RANSP-xPT: F-15666: ALPT -Enable Logical replication - S3 Buckets Creation | DC5-Sprint 2 | 5 | Rajender | NTSWSK-10061, | SOW
| RANSP-xPT: F-15666: ALPT - Enable Logical replication - Eanble memsql Pipelines for all tables | DC5-Sprint 2 | 5 | KM | NTSWSK-10062,
| RANSP-xPT: F-15666: ALPT - Enable Logical replication - Validate Loading cluster data is syncing with Reporting cluster | DC5-Sprint 2 | 5 | Pavan | NTSWSK-10063, | Vz
| RANSP-xPT: F-15666: ALPT - Validate MS with Reporting clsuter | DC5-Sprint 2 | 5 | Sourav | NTSWSK-10064, | Vz
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders Nokia | DC5-Sprint 3 | 2 | Karthik Kumar | NTSWSK-10053, | TCS
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders Ericsson | DC5-Sprint 3 | 2 | Ben | NTSWSK-10054, | TCS
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders- Samsung | DC5-Sprint 3 | 2 | Anand R | NTSWSK-10055, | Vz
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Corning | DC5-Sprint 3 | 2 | Anandh S | NTSWSK-10056, | Vz
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Core 5GC | DC5-Sprint 3 | 1 | Anandh S | NTSWSK-10057, | Vz
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Core EPC | DC5-Sprint 3 | 2 | Santa | NTSWSK-10058, | Vz
| RANSP-xPT: F-15666: UAT RF Sanity Validation for only Decoders-Cisco and epdg | DC5-Sprint 3 | 1 | Anandh S | NTSWSK-10059, | Vz
RANSP-xPT: CICD Pipeline stabilization and Bug fixes | RANSP-xPT: F-20008: CICD Stabilization - Parser | DC5-Sprint 1 | 3 | Sourav | NTSWSK-12242, | Vz
| RANSP-xPT: F-20008: CICD Stabilization - 4GMS | DC5-Sprint 1 | 2 | Sourav | NTSWSK-12243, | Vz
| RANSP-xPT: F-20008: CICD Stabilization - 5G RAN MS | DC5-Sprint 2 | 2 | Sourav | NTSWSK-12244, | Vz
| RANSP-xPT: F-20008: CICD Stabilization - 5G Core MS | DC5-Sprint 2 | 3 | Sourav | NTSWSK-12245, | Vz
| RANSP-xPT: F-20008: CICD Stabilization - UI | DC5-Sprint 3 | 2 | Sourav | NTSWSK-12246 | Vz
RANSP-xPT: Bulk Formula Update (UI & MS) - Analysis and DEV and Testing | RANSP-xPT: F-15689: Bulk Formula Update - Analysis | DC5-Sprint 1 | 5 | Sai | NTSWSK-10023,
| RANSP-xPT: F-15689: Bulk Formula Update - UI Changes | DC5-Sprint 2 | 5 | Gowtham | NTSWSK-10024,
| RANSP-xPT: F-15689: Bulk Formula Update - MS Changes for Template Download | DC5-Sprint 1 | 5 | Sai | NTSWSK-10025,
| RANSP-xPT: F-15689: Bulk Formula Update - MS changes on formula submission | DC5-Sprint 2 | 8 | Sai | NTSWSK-10026,
| RANSP-xPT: F-15689: Bulk Formula Update - MS Unit Test Case changes on formula submission | DC5-Sprint 3 | 2 | Sai | NTSWSK-10027,
| RANSP-xPT: F-15689: Bulk Formula Update Dev and SIT deployment - UI Integration | DC5-Sprint 3 | 3 | Sai | NTSWSK-10028,
| RANSP-xPT: F-15689: Bulk Formula Update Dev and SIT deployment - Regression testing | DC5-Sprint 3 | 2 | Suresh | NTSWSK-10029,
| RANSP-xPT: F-15689: Bulk Formula Update Dev and SIT deployment - MS & UI | DC5-Sprint 3 | 2 | Sai | NTSWSK-10030
32
RANSP-XPT-CICD pipeline for Cronverisioning-Prod and Parser- UAT | RANSP-xPT: F-20008 Crontab Versioning - Gather the multiple server cron data from Prod server | DC5-Sprint 1 | 3 | Raiyan
| RANSP-xPT: F-20008-Crontab Versioning - Run and validate the prod pipeline with collective server | DC5-Sprint 1 | 3 | Raiyan
| RANSP-xPT: F-20008-Parser versioning - Analysis the prod structure for pipeline design | DC5-Sprint 2 | 2 | Raiyan
| RANSP-xPT: F-20008-Parser versioning - Create a master structure based on Parser region, vendor and server | DC5-Sprint 2 | 2 | Raiyan
| RANSP-xPT: F-20008-Parser versioning - Prod parser configs data into SCM | DC5-Sprint 1 | 3 | Victory
| RANSP-xPT: F-20008Parser versioning - Create a pipeline script for the prod parser config | DC5-Sprint 3 | 3 | Raiyan
| RANSP-xPT: F-20008-Parser versioning - Validate the Prod env pipeline - intiate from UAT | DC5-Sprint 3 | 3 | Raiyan
| RANSP-xPT: F-20008-Regression job email issue support and changes - Adhoc | DC5-Sprint 1,2 | 3 | Raiyan
Sprint 1 261
Sprint 2 233
sprint 3 120
DC-5.2
| RANSP-xPT: F-18930: 4g WebSVC GET to POST- JUnit Test Cases | DC5-Sprint 2 | 1 | Praveen
| RANSP-xPT: F-18930: 4g WebSVC GET to POST- Regression SIT | DC5-Sprint 2 | 3 | Praveen | NTSWSK-11559,
Migrate 4G APIs from GET to POST - Phase 2 - UAT, MOP and Prod Deployment | RANSP-xPT: F-18934: Create a deployment YAML for UAT and deploy | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11560,
| RANSP-xPT: F-18934: - UAT Validation - Test the POST Controller against the existing GET controller response | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11561,
| RANSP-xPT: F-18934: - Create the MOP for the 4g WebSVC GET to POST deployment | DC5-Sprint 2 | 1 | Praveen | NTSWSK-11562,
| RANSP-xPT: F-18934: - Production Deployment - 4g WebSVC GET to POST - Tracker | DC5-Sprint 2 | 1 | Praveen | NTSWSK-11563,
| RANSP-xPT: F-18934: Regression testing | DC5-Sprint 2 | 2 | Suresh | NTSWSK-11564
| RANSP-xPT: F-18907: Ericsson 5G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 2 | 2 | Manju | NTSWSK-11311 | In Progress
RANSP-xPT: Ericsson EBSN 24Q4 decoder - Specs, Development, tetsing | RANSP-xPT: F-18912: Ericsson EBSN 24Q4 Decoder - Development (Parser , Loader Development&DBA Validation) | DC5-Sprint 2 | 2 | Praveen | NTSWSK-11362
Subscription Service APP_ACTIVITIES_LOG query changes | RANSP-xPT: F-20006: Subscription Service APP_ACTIVITIES_LOG query changes -Ofshore Dev/SIT environment testing | DC5-Sprint 2 | 3 | Praveen | NTSWSK-12278
RANSp-xPT: MUI Migration - unit testing- Setup and Structure adhoc | RANSP-xPT: F-20002: Unit Test Cases for Alpt form | DC5-Sprint 2 | 3 | Manju | NTSWSK-12403,
| RANSP-xPT: F-20002: Unit Test Cases for Dropdown file | DC5-Sprint 2 | 5 | shashikiran | NTSWSK-12405, | In Progress
| RANSP-xPT: F-20002: Unit Test cases for thresholdEntry, thresholdGroup, thresholdHelp,thresholdModal | DC5-Sprint 2 | 3 | Shashikiran | NTSWSK-12408,
| RANSP-xPT: F-20002: Unit Test cases for ReportActions | DC5-Sprint 2 | 2 | Manju | NTSWSK-12413,
| RANSP-xPT: F-20002: Unit Test cases for ReportReducers | DC5-Sprint 2 | 2 | Manju | NTSWSK-12414
RANSP-xPT: 5G Dual cluster Reporting Cluster Prepartion - Phase 1 | RANSP-xPT: F-18921: Identify all the samsung Relates table | DC5-Sprint 2 | 2 | Vijay | NTSWSK-11532,
| RANSP-xPT: F-18921: Prepare patch with Samsung tables and deploy in PT5GX | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11533, | In Progress
RANSP-xPT:Setup Reporting Cluster for UAT DB Extractor and Ingestor | RANSP-xPT: F-18940: Create all Required Db artifacts in ALPTX and ALPT_CENTRAL(Table,procedures,Views) | DC5-Sprint 2 | 3 | Arun | NTSWSK-11570,
| RANSP-xPT: F-18940: Load all the required metadata in reporting cluster | DC5-Sprint 2 | 2 | Arun | NTSWSK-11571,
| RANSP-xPT: F-18940: Create required Pipelines | DC5-Sprint 2 | 2 | Arun | NTSWSK-11572,
RANSP-xPT: F-18927:RANSP-xPT:Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- PROD | RANSP-xPT: F-18927: Add Hooks to deduplicate 15mintues loads in "No Aggregation" Mode for PT5G- Mop Creation | DC5-Sprint 2 | 1 | Vijay | NTSWSK-11548,
RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Analysis | RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- Patch Preparation | DC5-Sprint 2 | 1 | Priya | NTSWSK-11577,
| RANSP-xPT: F-18942: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ALPT- UAT Deployment | DC5-Sprint 2 | 1 | KrishnaReddy | NTSWSK-11578,
RANSP-xPT:Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-Analysi,Development,Testing-ELPT and PT5G | RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Analysis | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11583,
| RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Development | DC5-Sprint 2 | 5 | Priya | NTSWSK-11584,
| RANSP-xPT: F-18948: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT And PT5G- Testing | DC5-Sprint 2 | 5 | Vijay | NTSWSK-11585,
RANSP-xPT:Add Date Modified column for OM_DATA_INTERVAL,DATA_LOAD_INTERVALS,REGION and MARKET Tables for 4G and 5G-Analysis,Development and Testing | RANSP-xPT: F-18952: Analyze the code changes and identify if any dependent changes for ALPT,ELPT and PT5G | DC5-Sprint 2 | 3 | Priya | NTSWSK-11592, | InProgress
| RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Development | DC5-Sprint 2 | 3 | Priya | NTSWSK-11593,
| RANSP-xPT: F-18952: Add Date Modified column for ODI,DLI,REGION and MARKET Tables for 4G and 5G- Testing | DC5-Sprint 2 | 2 | Vijay | NTSWSK-11594,
RANSP-xPT:SdpProcessDailyDatabyRegion-Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries for ELPT-UAT | RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Development | DC5-Sprint 2 | 3 | Vijay | NTSWSK-11601,
| RANSP-xPT: F-18956: Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-Testing | DC5-Sprint 2 | 2 | Priya | NTSWSK-11602,
M-5490 F-15709-RANSP-xPT: Parserless Architecture-Filter and calucation of refactor engine-Analysis and Design- Phase-1 | RANSP-xPT:F-15709: Update script to generate flat and grouped nested JSON files. Description - Grouped Nested JSON File (With Hierarchy), Single File for Each Group (Counter Family) with Nested Hierarchy, Single File for Each Group (Counter Family) with Flat Json, Single Flat Json with Keys | DC5-Sprint 2 | 5 | Karthic | NTSWSK-10563, | Done | Incedo
M-5488 F-15710-RANSP-xPT: Reporting engine memory reduction-Analysis and Design-Phase-1 | RANSP-xPT: F-15710 Analysis - Report engine memory reduction Description - Analyse the possible scope in report engine that is consuming memory with the intent of speeding up the engine. (Thread profiling etc.,) | DC5-Sprint 2 | 5 | Karthic | NTSWSK-10555, | In Progress | Incedo
| RANSP-xPT: F-15710 POC for memory reduction & speeding up reports based on analysis | DC5-Sprint 2 | 3 | Praveen | NTSWSK-10556, |  | Incedo
M-5488 F-15711-Reporting engine work load management-Analysis and Design-Phase-1 | RANSP-xPT: F-15711: Analysis - Report engine work load management Description - When report generation is triggered from UI manage the load such that the report engine doesn't slow down or crashes | DC5-Sprint 2 | 5 | Atchutha | NTSWSK-10559, | In progress | Incedo
| RANSP-xPT: F-15711: POC for handling huge and multiple reports based on analysis | DC5-Sprint 2 | 3 | Atchutha | NTSWSK-10560, |  | Incedo
M-5246 F-15591- RANSP-xPT:5G ERC 24Q4 and vRAN 24.11 Decoder -UAT, MOP and Prod deployment-Phase 2 | RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decoder - 24Q2 - MOP creation-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-10240,
| RANSP-xPT:F-15591: 5G ERC 24Q4 and vRAN 24.11 Decode- 24Q2 -Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-10243
M-5246 F-15706 RANSP-xPT:Erc EBSN 24Q3 Decoder- Part 4 -Testing, UAT, MOP and Deployment - Phase-2 | RANSP-xPT: F-15706: Erc EBSN 24Q3 Decoder- Part 4 - 24Q3 - MOP creation- | DC5-Sprint 2 | 1 | Bala | NTSWSK-9645,
| RANSP-xPT: F-15592: Corining 4G 24.4 - - MOP creation- | DC5-Sprint 2 | 1 | Bala | NTSWSK-9635,
| RANSP-xPT: F-15592: Corining 4G 24.4 --Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9637,
M-5319 F-15593 RANSP-xPT: Corining 5G 24.4 -UAT,MOP and deployment-Phase-2 | RANSP-xPT: F-15593: Corining 5G 24.4 - - MOP creation-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9641,
| RANSP-xPT: F-15593: Corining 5G 24.4 --Parser and Loader Readiness-UAT | DC5-Sprint 2 | 1 | Bala | NTSWSK-9643,
RANSp-xPT: Regression test cases to be modified for MUI for RAN and Cross Vendor - Development & Testing | RANSP-xPT: F-19998: Verify one market selection should not give multiple markets SAH - report level: market, report type: hourly | DC5-Sprint 2 | 2 | suresh | NTSWSK-14186,
| RANSP-xPT: F-19998: Verify one market selection should not give multiple markets Report Builder - report level: market, report type: hourly | DC5-Sprint 2 | 2 | suresh | NTSWSK-14187,
| RANSP-xPT: F-19998: Verify Threshold filter check | DC5-Sprint 2 | 2 | suresh | NTSWSK-14188,
| RANSP-xPT: F-19998: Verify Cell group upload csv file check | DC5-Sprint 2 | 2 | suresh | NTSWSK-14189,
| RANSP-xPT: F-19998: Verify Specail KPI Traffic should not be zero or negative | DC5-Sprint 2 | 2 | Gowtham | NTSWSK-14194,
| RANSP-xPT: F-19998: Verify Export file csv and excel | DC5-Sprint 2 | 2 | Gowtham | NTSWSK-14195,
| RANSP-xPT: F-19998: Verify Content getting loaded after report selection is made in SAH Page | DC5-Sprint 2 | 1 | Gowtham | NTSWSK-14196,
| RANSP-xPT: F-15689: Bulk Formula Update - UI Changes | DC5-Sprint 2 | 5 | Gowtham | NTSWSK-10024,
| RANSP-xPT: F-15689: Bulk Formula Update - MS changes on formula submission | DC5-Sprint 2 | 8 | Sai | NTSWSK-10026,
RANSP-XPT-CICD pipeline for Cronverisioning-Prod and Parser- UAT | RANSP-xPT: F-20008-Parser versioning - Analysis the prod structure for pipeline design | DC5-Sprint 2 | 2 | Raiyan | NTSWSK-14279,
| RANSP-xPT: F-20008-Parser versioning - Create a master structure based on Parser region, vendor and server | DC5-Sprint 2 | 5 | Raiyan | NTSWSK-14280,
RANSP-xPT:SdpProcessDailyDatabyRegion-Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries for ELPT-PROD | RANSP-xPT:F-24290- Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-UAT Validation | DC6-Sprint 2 | 1 | Vijay
| RANSP-xPT:F-24290- Include OM_DAILY_LOAD_STATUS and OM_DAILY_STATUS Table Entries in SdpProcessDailyDatabyRegion- for ELPT-MOP Creation | DC6-Sprint 2 | 1 | Priya
RANSP-xPT:RANSP-xPT:Adding available and missing groups for ValidateMarketDailyReportReadiness for subscription-Analysis,Development,Testing For ELPT | RANSP-xPT:F-24280-Make all the required Procedural changes to Adding available and missing groups for ValidateMarketDailyReportReadiness for subscription-Development for ELPT | DC6-Sprint 2 | 2 | Vijay
| RANSP-xPT:F-24280-Make all the required tables and functional changes to Adding available and missing groups for ValidateMarketDailyReportReadiness for subscription-Development for ELPT | DC6-Sprint 2 | 5 | Vijay
RANSP-xPT:Implement changes to Daily Rollup so as to re-run if hourly has changed--PT5G-Analysis,Devlopement,Testing | RANSP-xPT:F-24285Make all the required procedural,Tables and functional changes to Implement changes to Daily Rollup so as to re-run if hourly has changed | DC6-Sprint 2 | 5 | Vijay
RANSP-xPT: DB patch automation enhancement | RANSP-xPT:F-24224- Parser config - prod pipeline config file test and validation | DC6-Sprint 2 | 3 | Raiyan
RANSP-xPT: Guardrails implementation for SAH and Webservices-4G | RANSP-xPT:F-24211- Guardrails implementation for SAH and Webservices-4G - MS Enhancement Phase II | DC6-Sprint 2 | 5 | manju
| RANSP-xPT:F-24211- Guardrails implementation for SAH and Webservices-4G - SIT Deployment/Testing | DC6-Sprint 2 | 3 | manju
TOTAL:-85
DC-6.3
RANSP-xPT: Ericsson 5G 25Q1 decoder - UAT, Prod deployment | RANSP-xPT: F-24202: Ericsson 5G 25Q1 decoder-Build Creation +MOP Creation + MOP Review | DC6-Sprint 3 | 1 | Bala
| RANSP-xPT: F-24202: Ericsson 5G 25Q1 decoder-- Prod Deployement | DC6-Sprint 3 | 1 | Bala
RANSP-xPT: Corning 5G 25.2 decoder - Development, SIT Validation, UAT, Prod | RANSP-xPT: F-24369: Corning 5G 25.2 decoder-Build Creation +MOP Creation + MOP Review | DC6-Sprint 3 | 1 | Bala
RANSP-xPT: Corning 4G 25.2 decoder - Development, SIT Validation, UAT, Prod | RANSP-xPT:F-24367: Corning 4G 25.2 decoder-Build Creation +MOP Creation + MOP Review | DC6-Sprint 3 | 1 | Bala
RANSP-xPT: Ericsson EBSN 25 Q1 decoder - Specs, Development, testing | RANSP-xPT: F-24202-Ericsson EBSN 5G 25Q1 Decoder - Development (Parser , Loader Development&DBA Validation) | DC6-Sprint 3 | 3 | Praveen
RANSP-xPT: Ericsson 4G 25Q2 decoder - Specs, Development, testing | RANSP-xPT:F-24585-Ericsson 4G 25Q2 decoder Decoder - Development (Parser , Loader Development&DBA Validation) | DC6-Sprint 3 | 3 | Atchuth
RANSP-xPT:Ericsson 5G 25Q2 decoder - Specs, Development, testing | RANSP-xPT: Ericsson 5G 25Q2 decoder Decoder - Development (Parser , Loader Development&DBA Validation) | DC6-Sprint 3 | 3 | Manju
RANSp-xPT: MUI Migration - unit testing - ReportWebservice,MyPreference,Header,Formula Editor | RANSP-xPT:F-24268-Unit test cases for Login | DC6-Sprint 3 | 5 | Shashikiran
| RANSP-xPT:F-24268-Unit test cases for Header | DC6-Sprint 3 | 5 | Shashikiran
RANSP-xPT: Tenable Agent Vulnerability Fix - Critical and High | RANSP-xPT:F-24234--Oracle Java JDK / JRE 6 < Update 30 Multiple Vulnerabilities (Unix) vulnerability fix | DC6-Sprint 3 | 5 | Arun
| RANSP-xPT:F-24234--Oracle Java SE Multiple Vulnerabilities (February 2013 CPU) (Unix) | DC6-Sprint 3 | 5 | Praveen
RANSP-xPT: Tenable Agent Vulnerability Fix - Medium and Low | RANSP-xPT:F-24231-Open JDK & Oracle JAVA version upgrades/remove | DC6-Sprint 3 | 5 | Atchuth
RANSp-xPT: Regression test cases to be modified for MUI for RAN - Phase 2 | RANSP-xPT:F-24274-Verify report builder report SPC 4G ELPT for MUI | DC6-Sprint 3 | 3 | Suresh
| RANSP-xPT:F-24274-Verify report builder report SPC 4G ALPT for MUI | DC6-Sprint 3 | 3 | Suresh
RANSP-xPT: 5G Dual cluster Reporting Cluster Prepartion - Phase 2 | RANSP-xPT:F-24302- Make all the required Procedural changes to support Dual cluster from ingestor side EPT5GX and SPT5GX | DC6-Sprint 3 | 5 | Vijay
| RANSP-xPT:F-24302-Prepare single patch to load all the XLPT Ingestor Artifacts(Tables,Procedures,Function,View and Pipelines) | DC6-Sprint 3 | 5 | KrishnaReddy
RANSP-xPT:Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-UAT -PT5G | RANSP-xPT: Expand-preserve-rawdata-to-capture-all-hours-and-additional-groups-ELPT- Mop Creation | DC6-Sprint 3 | 1 | Priya
RANSP-xPT:RANSP-xPT:Adding available and missing groups for ValidateMarketDailyReportReadiness for subscription-Analysis,Development,Testing For ELPT | RANSP-xPT:F-24280-Adding available and missing groups for ValidateMarketDailyReportReadiness for subscription-Testing for ELPT | DC6-Sprint 3 | 2 | Priya
RANSP-xPT:Implement changes to Daily Rollup so as to re-run if hourly has changed--PT5G-Analysis,Devlopement,Testing | RANSP-xPT:F-24285-Implement changes to Daily Rollup so as to re-run if hourly has changed-Testing | DC6-Sprint 3 | 2 | Priya
RANSP-xPT: Guardrails implementation for SAH and Webservices-4G | RANSP-xPT: F-24211Guardrails implementation for SAH and Webservices-4G - Unit test cases | DC6-Sprint 3 | 5 | Praveen
| RANSP-xPT:F-24211 Guardrails implementation for SAH and Webservices-4G - MOP and Deployment | DC6-Sprint 3 | 1 | Atchutha
| RANSP-xPT:F-24211 Guardrails implementation for SAH and Webservices-4G - Regression | DC6-Sprint 3 | 3 | Suresh
| RANSP-xPT:F-24211 Guardrails implementation for SAH and Webservices-4G - UAT Deployemnt/Testing | DC6-Sprint 3 | 3 | Praveen
TOTAL :- 71

## Sheet6
e | Sub Project | DC/Quater | Sprint | Activity | SDLC | AI Tool | Type of Work | Tech Stack | Feature/JIRA | Develper | Onshore/Offshore | Accuracy | Efficiency | Effort without AI(SPs) | Effort with AI(SPs) | #REF! | Issues/Challenges/Remark | Prompt Used
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | Gemini | New | Reactjs | NTSWSK-12401 | Gowtham | Offshore | 50% | 25% | 5 | 4 | 1 |  | Gems Added in th GDrive
XPT |  | DC5 | DC5.1 | Unit testcases | Testing | Gemini | New | Reactjs | NTSWSK-12402 | Gowtham | Offshore | 50% | 25% | 3 | 2 | 1 |  | Gems Added in th GDrive
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Suresh | Offshore | 40% | 30% | 2 | 1.5 | 0.5 | Helped in accelerating the process and complete the story quickly
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | suresh | Offshore | 30% | 25% | 2 | 1.5 | 0.5 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | suresh | Offshore | 35% | 20% | 2 | 1.75 | 0.25 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | suresh | Offshore | 35% | 15% | 2 | 1.75 | 0.25 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | suresh | Offshore | 20% | 25% | 2 | 1.75 | 0.25 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 35% | 25% | 2 | 1.75 | 0.25 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 40% | 30% | 2 | 1.75 | 0.25 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 35% | 30% | 1 | 0 | 0 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC5 | DC-5.2 | Development | Development | Gemini | old | React Js | NTSWSK-10024, | Gowtham | Offshore | 35% | 25% | 5 | 4 | 1 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path | Promt Added in the Gdive(react.txt)
XPT |  | DC-5 | DC-5.3 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 35% | 35% | 2 | 1.5 | 0.5 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC-5 | DC-5.3 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 25% | 25% | 2 | 1.5 | 0.5 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC-5 | DC-5.3 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Gowtham | Offshore | 35% | 30% | 2 | 1.5 | 0.5 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC-5 | DC-5.3 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Suresh | Offshore | 35% | 30% | 2 | 1.5 | 0.5 | Helped in getting the initial structure of code but later need to replace with our application x-pathHelped in getting the initial structure of code but later need to replace with our application x-path
XPT |  | DC-6 | DC-5.3 | Code-Review | Code-Review | Gemini | new | Javascript | NTSWSK-10025 | Suresh | offshore | 40% | 40% | 2 | 1 | 1
XPT |  | DC-6 | DC-5.2 | React | Development | Gemini | Old | React Js | NTSWSK-9922, | Gowtham | offshore | 40% | 40% | 5 | 4 | 1 | Gave the Logic But need to update with canvas story book
XPT |  | DC-7 | DC-5.1 | Regression | Testing | Gemini | New | Cypress,Javascript | F-15667 | Suresh | offshore | 30% | 25% | 5 | 4 | 1
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Design | gemini | New | Reactjs RTL | NTSWSK-12400, | Shashikiran | Offshore | 50% | 25% | 2 | 1.8 | 0.2 | as per our Project code base its not giving the proper code here we need to tweek it
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12409, | Shashikiran | Offshore | 80% | 80% | 2 | 1..5 | 0.5 | setState is and Few methods it not getting covered | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12410, | Shashikiran | Offshore | 100% | 85% | 2 | 1.5 | 0.5 |  | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | gemini | New | Reactjs RTL | NTSWSK-12411, | Shashikiran | Offshore | 70% | 70% | 3 | 2 | 1 |  | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Code-Review | Code-Review | gemini | New | Reactjs RTL | NTSWSK-12412, | Shashikiran | Offshore |  |  | 2 | 1 | 0.5 |  | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12404, | Manju | Offshore | 70% | 30% | 3 | 2 |  | Since AI doesnt have idea in regard with local configuration configuration, There is no much accuracy. Co-Pilot may fill this gap | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC5.1 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12407, | Manju | Offshore | 70% | 50% | 3 | 2 |  | Got the errors , Can be resolved when gone through whole component . Debugging efforts to get the dummy test data related tp props, state despite the use of AI | Gems attached in G-Drive
XPT | RAN2 | DC5 | DC-5.2 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12405, | shashikiran | Offshore | 80% | 70% | 5 | 1 |  | if lese condtion and setState methods are not getting covered | DC5/DC5.1/SimpleRTLPrompt
XPT | RAN2 | DC5 | DC-5.2 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12408, | Shashikiran | Offshore | 70% | 55% | 3 |  |  | if lese condtion and setState methods are not getting covered | DC5/DC5.1/SimpleRTLPrompt
XPT | RAN2 | DC5 | DC-5.2 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12413, | Manju | Offshore | 60% | 75% | 2 | 1.5 | 0.5 | Since AI doesnt have idea in regard with local configuration configuration, There is no much accuracy. Co-Pilot may fill this gap | Gems/RTLGem
XPT | RAN2 | DC5 | DC-5.2 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12414 | Manju | Offshore | 60% | 70% | 2 | 1.5 | 0.5 |  | DC5/DC5.1/SimpleRTLPrompt
XPT | RAN2 | DC5 | DC-5.2 | Unit testcases | Testing | Unit testcases | New | Reactjs RTL | NTSWSK-12403 | Manju | Offshore | 55% | 60% | 3 | 2 | 1 | Loops and More lines of code | DC5/DC5.1/SimpleRTLPrompt
| RAN2 | DC5 |  | Unit testcases | Testing | Unit testcases | New | Java - Operational | NTSWSK-11311 | Manju |  |  |  | 1
| RAN2 | DC5 |  | Unit testcases | Testing | Unit testcases | New | Java - Operational | NTSWSK-11354 | Manju |  |  |  | 1
XPT | RAN2 | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | NTSWSK-11311 | Manju |  | - | - | 2 |  |  |  | MemSql_prompt
XPT | RAN2 | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | NTSWSK-11354 | Manju |  | - | - | 2 |  |  |  | MemSql_prompt
XPT | RAN2 | DC-5 | DC-5.3 | Decoder | Development | - | Old | Java - Operational | Ericsson EBSN 25Q1 | Manju |  | - | - | 2 |  |  |  | MemSql_prompt
XPT | RAN2 | DC-5 | DC-5.3 | unit test cases | Testing | Unit testcases | new | Reactjs RTL | NTSWSK-12406, | Shashikiran |  | 85% | 80% | 8 |  |  |  | DC5/DC5.1/SimpleRTLPrompt
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java | NTSWSK-10559 | AtchuthaSai | Offshore | 50% | 50% | 3 | 2 | 2 | Refactoring code changes and also find out time between old and new code
XPT |  | DC5 | DC5.1 | Code Analysis | Development | Gemini | New | Java | NTSWSK-10023 | AtchuthaSai | Offshore | 40% | 4% | 3 | 2 | 2 | For this story , with the help of this AI finding some classes and generated excel reports
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | Java | NTSWSK-10560, | AtchuthaSai | Offshore | 50% | 50% | 3 | 1 | 1 | Calculating some bussiness logics time | How to calculate the time between particular code?
|  | DC5 | DC-5,.2 | Analysis | Development | gemini | New | Java | NTSWSK-10026, | AtchuthaSai | Offshore | 30% | 30% | 8 | 1 | 1 | Generate some bussiness logics code | Implemented some bussiness logics according to requirements
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | Java | NTSWSK-10557 | AtchuthaSai | Offshore | 50% | 50% | 5 | 2 | 2 | Refactoring some bussiness logics | Converting old logics to new logics code
XPT |  | DC5 | DC-5.3 | Analysis | Development | gemini | New | Java | NTSWSK-10559, | Atchutha | Offshore | 30% | 30% | 5 | 2 | 2 | Analaysis on the old code using GEN AI | I used in reportEngine functionality Analasis
XPT |  | DC5 | DC-5.3 | Code Developmet | Development | gemini | New | Java | NTSWSK-10560, | Atchutha | Offshore | 40% | 40% | 3 | 1 | 1 | Converted some old bussiness logics to new bussiness logics using GEN AI | I used poc for report Engine functionality
XPT |  | DC5 | DC5.1 | Documantation | Design | gemini | New | Java | NTSWSK-12274, | Praveen | Offshore | 70% | 80% | 2 | 1.5 | 0.5 | As per given requrement it generated on my given inputs in propessional way
XPT |  | DC5 | DC5.1 | Code Optimazation | Development | gemini | New | Java | NTSWSK-12275, | Praveen | Offshore | 70% | 50% | 5 | 4 | 1 | Need to debug the code and apply the manually logic in existing code according to our requirement
XPT |  | DC5 | DC-5.2 | Unit testcases | Testing | Gemini | New | Java | RANSP-xPT: F-18930 | Praveen | Offshore | 70% | 60% | 1 | 0.5 | 0.5 | after using genai getting good covered
XPT |  | DC5 | DC-5.2 | Code Developmet | Development | Gemini | New | Java | NTSWSK-11559, | Praveen | Offshore | 60% | 70% | 3 | 2 | 1
XPT |  | DC5 | DC-5.2 | Documentation | Deployment | Gemini | New | Java | NTSWSK-11560, | Praveen | Offshore | 50% | 40% | 2 | 1.5 | 0.5
XPT |  | DC5 | DC-5.2 | Validation | Testing | Gemini | New | Java | NTSWSK-11561, | Praveen | Offshore | 40% | 30% | 2 | 1.5 | 0.5
XPT |  | DC5 | DC-5.2 | Documentation | Deployment | Gemini | New | Java | NTSWSK-11562, | Praveen | Offshore | 40% | 30% | 1 | 1 | 0
XPT |  | DC5 | DC-5.2 | Decoder | Deployment | Gemini | Old | Java | NTSWSK-11362 | Praveen | Offshore | 30% | 10% | 2 | 2 | 0
XPT |  | DC-5 | DC-5.3 | Analysis | Development | gemini | New | Java | NTSWSK-10556, | Praveen | Offshore | 60% | 40% | 3 | 2 | 1 | Analyzed the Existing code and idenfied the some bussiness logics who takes more time and also finding the solution | Converting old logics to new logics code
XPT |  | DC5 | DC5.1 | Test cases | Testing | gemini |  | MemSQL | NTSWSK-11550 | Priya | Offshore | 50% | 40% | 1 | 1 |  | Got the test case for a SP to be tested
XPT |  | DC5 | DC-5.2 | Deployment | Deployment | gemini | new | MemSql | NTSWSK-11577, | Priya | Offshore | 40% | 20% | 1 | 0.5
XPT |  | DC5 | DC-5.2 | Deployment | Deployment | gemini | new | MemSql | NTSWSK-11584, | Priya | Offshore | 35% | 40% | 5 | 4
XPT |  | DC5 | DC-5.2 | Analysis | Analysis | gemini | New | MemSql | NTSWSK-11592, | Priya | Offshore | 60 | 50 | 3 | 2 | 1 |  | I need the specific SQL queries and steps for SingleStore (MemSQL) to analyze changes to a table schema when a new column is added. The output should identify potentially affected views, stored procedures, functions, triggers, and foreign key constraints. For each, provide the SQL query, explain how to interpret the results, and suggest necessary modifications.
XPT |  | DC5 | DC-5.2 | Analysis | Development | gemini | New | MemSql | NTSWSK-11593, | Priya | Offshore | 90 | 100 | 3 | 1 | 2 | Using this prompt we updated for seven tables | Please provide the SQL ALTER TABLE ADD COLUMN statement for SingleStore (MemSQL) to add a timestamp column. The new column should have microsecond precision, automatically default to the current timestamp on insertion, and automatically update to the current timestamp whenever the row is modified. Use placeholders for the table name and the new column name
XPT |  | DC5 | DC-5.2 | Development | Development | gemini | New | MemSql | NTSWSK-11602, | Priya | Offshore | 30% | 10% | 2
XPT |  | DC5 | DC-5.2 | Development | Development | gemini | New | MemSql |  | Priya | Offshore | 40% | 20% | 1
[9 empty] | NTSWSK-11602 | Priya
[9 empty] | NTSWSK-11584 | Priya
[9 empty] | NTSWSK-11603 | Priya |  |  |  | 1
[9 empty] | NTSWSK-11534, | Priya |  | 70% | 85% | 2
[9 empty] | NTSWSK-11535, | Priya |  | 60% | 70% | 3